## Review Findings
Legend:
1 to 30 days
31 to 60 days
* Please do not paste the findings in the row provided. Istead use Paste Special -> Values | [7 empty] | 61 to 180 days
> 180 days
Review Findings
ID No. | Document Name | Description | Defect Acceptance | Log Date | Closure Date | Status | Ageing (Days) | Comments (If any)
1 | AUM Implemention Proposal | To bring in the Context of the Module, where does it fit in, and what other it talk to etc, A diagram needed - Page 3 | Accepted | 2018-06-05 |  | Closed | 9 | Done
2 | AUM Implemention Proposal | Role Management - Page 3 | Accepted | 2018-06-05 |  | Closed | 9 | Role Management will be part of UAM Interface
3 | AUM Implemention Proposal | Making the document gender neutral - Page 3 | Accepted | 2018-06-05 |  | Closed | 9 | Done
4 | AUM Implemention Proposal | Master Reset - Page 3 | Deferred | 2018-06-05 |  | Open | 9 | Functionality is yet to be finalized
5 | AUM Implemention Proposal | Role Info | Accepted | 2018-06-05 |  | Closed | 9 | Role Info will be maintained at the SQLite DB of UAM application.
6 | AUM Implemention Proposal | UserName,Password Storage - Page 4 | Accepted | 2018-06-05 |  | Closed | 9 | Password will be Hashed using SHA256 Salt algorithm and stored in the SQLite DB. Username will not be used in the application as we have decided to use EmailID for Login
7 | AUM Implemention Proposal | Forgotten Password - Page 5 | Deferred | 2018-06-05 |  | Open | 9 | Functionality is yet to be finalized
8 | AUM Implemention Proposal | Caption and Number the diagram - Page 6 | Accepted | 2018-06-05 |  | Closed | 9 | Done
9 | AUM Implemention Proposal | Unlock User Account - Page 6 | Deferred | 2018-06-05 |  | Open | 9 | Functionality is yet to be finalized
10 | AUM Implemention Proposal | Secret Question - Page 6 | Deferred | 2018-06-05 |  | Open | 9 | Functionality is yet to be finalized
11 | AUM Implemention Proposal | Mechanism for Master Reset - Page 6 | Deferred | 2018-06-05 |  | Open | 9 | Functionality is yet to be finalized
12 | AUM Implemention Proposal | Password Rules - Page 6 | Accepted | 2018-06-05 |  | Closed | 9 | Provided the description at the diagram. Password Rules will of Min Length, Max Length, Character specification will be handled at the UI
13 | AUM Implemention Proposal | Role Management - Page 7 | Accepted | 2018-06-05 |  | Closed | 9 | Role and Activity Management will be handled at the DB Level.
14 | AUM Implemention Proposal | Password Storage - Page 12 | Accepted | 2018-06-05 |  | Closed | 9 | Password will be Hashed using SHA256 Salt algorithm and the same will be stored in table
15 | AUM Implemention Proposal | Listing Open Source Components - Page 16 | Accepted | 2018-06-05 |  | Closed | 9 | No Open source components are used in the application
16 | AUM Implemention Proposal | To provide estimations for OSS Scan, Cyber security Checklist filling and support to Mini, and Integration Test - Page 17 | Accepted | 2018-06-05 |  | Closed | 9 | Provided the estimates for these components
Formulas:
Ageing (Days) = IF(IF([Closure Date]="",TODAY()-[Log Date],[Closure Date]-[Log Date])>10000,"",IF([Closure Date]="",TODAY()-[Log Date],[Closure Date]-[Log Date]))