## Review Findings
Legend:
1 to 30 days
31 to 60 days
* Please do not paste the findings in the row provided. Istead use Paste Special -> Values | [7 empty] | 61 to 180 days
> 180 days
Review Findings
ID No. | Document Name | Description | Defect Acceptance | Log Date | Closure Date | Status | Ageing (Days) | Comments (If any)
1 | AUM Implemention Proposal | Rename the Title and to delete the Hidden Text Page 1 | Accepted | 2018-05-30 |  | Closed | 15 | Done
2 | AUM Implemention Proposal | Footer Corrections: Author, External Document No., Project ID, Approvar, Doc Kind, Title, Rev. ind, Doc No. - Page 1 | Accepted | 2018-05-30 |  | Open | 15 | Yet to get the Document Name, Approver details from Akshya
5 | AUM Implemention Proposal | Summary Correction & To add "for UAM" for point 6 -: Page 3 | Accepted | 2018-05-30 |  | Closed | 15 | Done
8 | AUM Implemention Proposal | Have removed the activities which are not part of UAM and for Role Access Rights - As there is no API level implementation have removed. It will be handled at the DB level | Accepted | 2018-05-30 |  | Closed | 15 | Have removed the Role Creation, Activity Creation and other Rights which are not getting handled at the API level
9 | AUM Implemention Proposal | To remove <Use Case Name> in the 3.1 Heading and to Move the 4.Heading to New Page - Page -11 | Accepted | 2018-05-30 |  | Closed | 15 | Done
10 | AUM Implemention Proposal | To remove the Topics which are not required like 4.4,4.5,4.6 and to provide inputs on 4.6 topic - Page 15 | Accepted | 2018-05-30 |  | Closed | 15 | Done
11 | AUM Implemention Proposal | 4.8 Reuse - to be filled and move Point 5 to next page- Page 16 | Accepted | 2018-05-30 |  | Closed | 15 | Done
12 | AUM Implemention Proposal | To add the reasons for the Technologies which will be used | Accepted | 2018-05-30 |  | Closed | 15 | Done
13 | AUM Implemention Proposal | Approach for Cyber security | Accepted | 2018-05-30 |  | Closed | 15 | Done
14 | AUM Implemention Proposal | Thought on Performance, Capacity and Usability | Accepted | 2018-05-30 |  | Closed | 15 | Done
15 | AUM Implemention Proposal | To add about the estimation methods and provide link to WBS document - Page 17 | Accepted | 2018-05-30 |  | Closed | 15 | Done
16 | AUM Implemention Proposal | Effort Estimation: Is unit testing covered here: | Rejected | 2018-05-30 |  | Closed | 15 | Covered as part of MSTestV2 which is a Unit testing frameword
17 | AUM Implemention Proposal | MSBuild: Every sprint needs to be built - every code checkin will be built, 8hrs is only for the Design, as the WBS is done the time is getting updated - Page 18 | Accepted | 2018-05-30 |  | Closed | 15 | Reestimated
18 | AUM Implemention Proposal | Cyber security and Integration Testing - Estimates - Page 18 | Accepted | 2018-05-30 |  | Closed | 15 | Done
19 | AUM Implemention Proposal | To deleted 8.2 Hardware part as its not required - Page 18 | Accepted | 2018-05-30 |  | Closed | 15 | Done
20 | AUM Implemention Proposal | To add IP Document, Unit Testing Report, Design Document related efforts in 8.3 document - Page 18 | Accepted | 2018-05-30 |  | Closed | 15 | Done
17 | AUM Implemention Proposal | To consider the Risks - in Page 20 | Accepted | 2018-05-30 |  | Closed | 15 | Done
18 | AUM Implemention Proposal | To add Reference | Accepted | 2018-05-30 |  | Closed | 15 | Done
Formulas:
Ageing (Days) = IF(IF([Closure Date]="",TODAY()-[Log Date],[Closure Date]-[Log Date])>10000,"",IF([Closure Date]="",TODAY()-[Log Date],[Closure Date]-[Log Date]))