## WBS & Estimation
WBS & Estimation
Project Name : | PBN ID : | Project manager :
AOA User Management |  | Vinay Kariwala
Link to Measurement Repository
Reference values considered from Measurement Repository | Metric Name | Values referred | Planned value for the project
PM Effort
CM Effort
Rework Effort
| Total Estimated Work: |  | 230 | (Person hours) |  |  |  |  | 0 | (days)
|  | Basis for Estimation |  |  | Estimated Person hours |  |  | Average Effort | Number of Persons | Duration (Calendar Days) |  |  | Comments (Assumptions, Constraints and Rationale for Estimation, if any)
Work Product | WBS Element (Activity, task, or sub-task) | Work Product Size | Unit of Measure | Complexity | Optimistic | Most Likely | Pessimistic |  |  |  | Phase | Task Type
Project Planning
Project Description & Plan
Draft ready for internal review
Internal review draft
Draft ready for external review
External review draft
Final version for approval
Steco Approval
WBS
Activity Plan
Draft ready for internal review
Internal review draft
Draft ready for external review
External review draft
Final version for approval
Steco Approval
Time Schedule (Gantt chart)
Draft ready for internal review
Internal review draft
Draft ready for external review
External review draft
Final version for approval
Steco Approval
Follow up/Plan other activities (processes)
Product Requirement Specification
Configuration Management (CM)
Quality Assurance (QA)
Type Test Plan (TTP)
Training Plan
Release Coordination with other products
Configuration Management (CM)
CM Plan
| Draft ready for internal review | Simple | No of Function Points | Low | 4 | 6 | 8 | 6 | 1 | 0.75 | Design | Configuration management | The Document to be prepared to list down the Steps involved in Deployment process and to be provided to SCM Team/Individual to follow
| Internal review draft | Simple | No of Function Points | Low | 2 | 2 | 2 | 2 | 1 | 0.25 | Design | Review | For the review from the team
Baseline Plan
Draft ready for internal review
Internal review draft
Draft ready for external review
External review draft
Final version for approval
Steco Approval
Version Specification
Quality Assurance (QA)
Quality Plan
Draft ready for internal review
Internal review draft
Draft ready for external review
External review draft
Final version for approval
Steco Approval
QA Review <n>
Quality Reports
PPQA reports
Reminder List
Outsource Management
Subcontracting Request
Purchase Requisition
Statement of Work
Project Monitoring & Control (Tracking)
Plans
Update Activity plan
Action Plan
Risk Plan
Reports
Project Report
xx
Project Meetings
Project Core Team Meeting
Project Group
Other
CCB
Gates
G2
preG3
G3
preG4
G4
preG5
G5
preG6
G6
Final Report
Draft ready for internal review
Internal review draft
Draft ready for external review
External review draft
Final version for approval
Steco Approval
Requirements Management and Control
Prepare Requirements Specification
Draft ready for internal review
Internal review draft
Draft ready for external review
External review draft
Final version for approval
Steco Approval
CR handling
Update PRS/FRS
Traceability
Technical Solution
Implementation Proposal
| Draft ready for internal review | Simple | No of Function Points | Low | 20 | 24 | 30 | 24.3333 | 1 | 3.0417 | Design | Project Planning | For the work remaining after review comments from Team
| Internal review draft | Simple | No of Function Points | Low | 6 | 8 | 10 | 8 | 1 | 1 | Design | Review | For the review from Team after the correction in the document
| Draft ready for WBS Document | Simple | No of Function Points | Low | 6 | 8 | 10 | 8 | 1 | 1 | Design | Project Planning | For the remaining WBS document preparation after the review comments from Team
| WBS Internal review | Simple | No of Function Points | Low | 2 | 2 | 3 | 2.1667 | 1 | 0.27083 | Design | Review | For the review from Team after the correction in the document
| Final version for approval | Simple | No of Function Points | Low |  |  |  | 0 | 1 | 0
[8 empty] | 0 | 1 | 0
System Architecture
| Draft ready for internal review | Simple | No of Function Points | Low | 8 | 10 | 12 | 10 | 1 | 1.25 | Design | Project Planning | Apart from the already prepared UMLs, Use Case Diagrams, and API Interfaces, this time is blocked for the future purpose which will be used during development phase for overall Design document preparation on the go during the development and Cyber security document(if needed)
| Internal review draft | Simple | No of Function Points | Low | 2 | 4 | 6 | 4 | 1 | 0.5 | Design | Project Planning | For the review from Team after the correction in the document
Component/Function <1> | User Component - Business Layer | Complex | KSLOC | High
Implementation <subfunction/component>
| AddUser | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | To insert the complete User Information and to log an entry in Audit Log which include C# Code development in BL & SQLite Query Creation
| DeleteUser | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | To delete the whole User Information and to log an entry in Audit Log which include C# Code development in BL & SQLite Query Creation
| UpdateUser | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | To update the User Information in the SQLite DB and to log an entry in Audit Log which include C# Code development in BL & SQLite Query Creation
| GetUser | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | To get the whole User Information from SQLite DB which include C# Code development and writing SQLite Queries
| IsPasswordExpired | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Coding | To know the User's password expiration from SQLite, which include C# Code development, SQLite Query Creation
| LockUserAccount | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | To lock the User account and to log an entry in Audit Log in the System, which include C# Code development, SQLite Query Creation
| MasterReset | Simple | KSLOC | Low | 4 | 6 | 8 | 6 | 1 | 0.75 | Implementation | Coding | To delete all the User related information and do a master reset and to log an entry in Audit Log, which include C# Code development, SQLite Query Creation. Considering the MasterReset of all the data from the system on the Pesimistic estimate
| NotifyforExpiration | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | Inserting the whole User Information into the SQLite Database which include C# Code development, SQLite Query Creation
| ResetPassword | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | Allowing the user to reset the password into the SQLite Database and to log an entry in Audit Log which include C# Code development, SQLite Query Creation
| SetPasswordExpirationDate | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Coding | Inserting the whole User Information into the SQLite Database which include C# Code development, SQLite Query Creation
| VerifyDuplicateEmailID | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Coding | To check whether the user table has already have the provided email
| LoginAuthentication | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | To authenticate the Username and Password towards various conditional checks like Password Expiration, Locked Account, Reset Password and to log an entry in Audit Log which include C# code and SQLite Query creation
| Unit Testing | Complex | KSLOC | Medium | 9 | 10 | 14 | 11.55 | 1 | 1.4438 | Implementation | Coding | Writing MSV2 unit test cases for the entire User Component which includes 10 methods. If Nunit is used we need to revisit this estimate
| Code Reviews | Simple | KSLOC | Low | 2 | 4 | 6 | 4 | 1 | 0.5 | Testing | Review | Code Reviews for 10 methods
| Rework/Bug fixing | Simple | KSLOC | Low | 7 | 8 | 10 | 8.1667 | 1 | 1.0208 | Implementation | Rework due to Defects | For Rework due to defects of 10 methods
| Integration Test | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Testing | To check the integration with UI application and the Back end application
| Code Coverage/Code Metrics | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Project Monitoring and Control | To get the report of Code Coverage for the User component
| Support to QE/Tester | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Testing | Testing | Support for the QE Testing activities
Component/Function <2> | Password Archive Component - Business Layer | Medium | KSLOC | Medium
Implementation <subfunction/component>
| AddUserPasswords | Simple | KSLOC | Low | 3 | 4 | 5 | 4 | 1 | 0.5 | Implementation | Coding | To keep the backup of User's password in the DB, which involves C# code and SQLite Query Creation
| GetUserPasswords | Simple | KSLOC | Low | 3 | 4 | 5 | 4 | 1 | 0.5 | Implementation | Coding | To get the list of last 3 user passwords which involves C# code and SQLite Query Creation
| ValidatePasswordHistory | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Coding | To restrict the user from using the last three passwords
| Unit Testing | Medium | KSLOC | Medium | 2 | 2 | 5 | 2.75 | 1 | 0.34375 | Implementation | Coding | Writing unit test cases for the entire Authentication Secret Component which includes 6 methods
| Code Reviews | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Review | Code Reviews for 6 methods
| Rework/Bug fixing | Simple | KSLOC | Low | 2 | 2 | 5 | 2.5 | 1 | 0.3125 | Implementation | Rework due to Defects | For Rework due to defects of 6 methods
| Integration Test | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Testing | To check the integration with UI application and the Back end application
| Code Coverage/Code Metrics | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Project Monitoring and Control | To get the report of Code Coverage for the Authentication Secret component
| Support to QE/Tester | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Testing | Support for the QE Testing activities
Component/Function <n> | Role Component | Medium | KSLOC | Medium |  |  |  | 0
0
0
| Implementation <subfunction/component> | [6 empty] | 0
| GetRole | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Coding | To get the List of Roles
| GetRoleActivityRight | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Coding | To get the list of activities associated to a role
| UserRoleMapping | Simple | KSLOC | Low | 2 | 4 | 6 | 4 | 1 | 0.5 | Implementation | Coding | To map the Role to a User and have a log entry in Audit log table
| GetUserActivityRights | Simple | KSLOC | Medium | 2 | 4 | 4 | 4.0333 | 1 | 0.50417 | Implementation | Coding | To get all the rights associated to the User with multiple roles associated
| Unit Testing | Simple | KSLOC | Medium | 3 | 4 | 6 | 4.5833 | 1 | 0.57292 | Implementation | Coding | Writing unit test cases for the entire Audit Secret Component which includes 3 methods
| Code Reviews | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Review | Code Reviews for 3 methods
| Rework/Bug fixing | Simple | KSLOC | Low | 2 | 2 | 6 | 2.6667 | 1 | 0.33333 | Implementation | Rework due to Defects | For Rework due to defects of 3 methods
| Integration Test | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Testing | To check the integration with UI application and the Back end application
| Code Coverage/Code Metrics | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Project Monitoring and Control | To get the report of Code Coverage for Audit Log component
| Support to QE/Tester | Simple | KSLOC | Low | 2 | 4 | 4 | 3.6667 | 1 | 0.45833 | Testing | Testing | Support for the QE Testing activities
Component/Function <n> | Audit Log - Business Layer | Medium | KSLOC | Medium
Implementation <subfunction/component>
| AddUserLogs | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | To insert the User's log in the SQLite DB which involves C# code and SQLite Query Creation
| GetUserLogs | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Coding | To get the User Logs, which involves C# Code and SQLite Query Creation
| Unit Testing | Simple | KSLOC | Medium | 2 | 2 | 6 | 2.6667 | 1 | 0.33333 | Implementation | Coding | Writing unit test cases for the entire Audit Secret Component which includes 3 methods
| Code Reviews | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Review | Code Reviews for 3 methods
| Rework/Bug fixing | Simple | KSLOC | Low | 2 | 2 | 6 | 2.6667 | 1 | 0.33333 | Implementation | Rework due to Defects | For Rework due to defects of 3 methods
| Integration Test | Simple | KSLOC | Low | 1 | 1 | 2 | 1.1667 | 1 | 0.14583 | Testing | Testing | To check the integration with UI application and the Back end application
| Code Coverage/Code Metrics | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Project Monitoring and Control | To get the report of Code Coverage for Audit Log component
| Support to QE/Tester | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Testing | Support for the QE Testing activities
Component/Function <n> | UM WEB API Interface | Simple | KSLOC | Medium
Implementation <subfunction/component>
| User Component API | Simple | KSLOC | Low | 6 | 8 | 10 | 8 | 1 | 1 | Implementation | Coding | To create the API interface and to have the right security at the API level and to implement the attribute routing. Considering no AD Authentication.
| Audit Log API | Simple | KSLOC | Low | 2 | 4 | 6 | 4 | 1 | 0.5 | Implementation | Coding | To create the API interface and to have the right security at the API level and to implement the attribute routing
| RBAC API | Simple | KSLOC | Low | 2 | 4 | 6 | 4 | 1 | 0.5 | Implementation | Coding | To create the API interface and to have the right security at the API level and to implement the attribute routing
| Unit Testing | Simple | KSLOC | Low | 4 | 4 | 8 | 4.6667 | 1 | 0.58333 | Implementation | Coding | Writing unit test cases for the entire API Interface which includes 3 major business components
| Code Reviews | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Review | Code Reviews for 3 API Interfaces
| Rework/Bug fixing | Simple | KSLOC | Low | 3 | 4 | 8 | 4.5 | 1 | 0.5625 | Implementation | Rework due to Defects | For Rework due to defects of 3 components
| Integration Test | Simple | KSLOC | Low | 6 | 8 | 10 | 8 | 1 | 1 | Testing | Testing | To check the integration with UI application and the Back end application
| Code Coverage/Code Metrics | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Project Monitoring and Control | To get the report of Code Coverage for 3 components API Interface
| Support to UI/UX Developer | Simple | KSLOC | Low | 4 | 6 | 8 | 6 | 1 | 0.75 | Testing | Testing | knowledge sharing to UI/UX developer on work flow
Component/Function <n> | MSBuild - Automated Build | Medium | KSLOC | Medium
Implementation <subfunction/component>
| Build Definition | Medium | KSLOC | Low | 8 | 10 | 12 | 10 | 1 | 1.25 | Implementation | Configuration management | To create the MSBuild Definition which needs exploration as well
| Creating Transformation files Web.Config(for QA/EVAL/PROD env) | Medium | KSLOC | Low | 4 | 6 | 8 | 6 | 1 | 0.75 | Implementation | Configuration management | To create the Transformation files which is required for QA/EVAL/PROD environments
| Build Package Creation | Simple | KSLOC | Medium | 2 | 4 | 6 | 4.4 | 1 | 0.55 | Implementation | Configuration management | To create the Build Package which needs an exploration from myside as well
| Automated Build Configuration | Medium | KSLOC | Low | 8 | 10 | 12 | 10 | 1 | 1.25 | Implementation | Configuration management | To configure the time and the frequency for the Build activity which needs exploration as well
| Build Activity Exploration | Simple | KSLOC | Low | 6 | 8 | 8 | 7.6667 | 1 | 0.95833 | Planning & Req Development | Project related Training | Overall build features exploration
| Implementation Reviews | Simple | KSLOC | Low | 2 | 4 | 6 | 4 | 1 | 0.5 | Testing | Review | Code and implementation review
| Rework/Bug fixing | Simple | KSLOC | Low | 7 | 8 | 12 | 8.5 | 1 | 1.0625 | Implementation | Rework due to Defects | For Rework due to review comments
Component/Function <n> | Cyber Security | Medium | KSLOC | Medium
Implementation <subfunction/component>
| Oauth implementation | Simple | KSLOC | Medium | 4 | 6 | 8 | 6.6 | 1 | 0.825 | Implementation | Coding | To implement Oauth
| SHA Algorithm Implementation | Simple | KSLOC | Medium | 12 | 16 | 18 | 17.2333 | 1 | 2.1542 | Implementation | Coding | To implement the SHA algorithm for the usage of Passwords across the entire application
| PlainText Encryption and Decryption | Simple | KSLOC | Low | 4 | 6 | 8 | 6 | 1 | 0.75 | Implementation | Coding | To encrypt the Webconfig Plaintext entries
| Secure Data Communication over HTTPS | Simple | KSLOC | Low | 2 | 4 | 6 | 4 | 1 | 0.5 | Implementation | Coding | To implement the HTTPPost and other related components to ensure the Secure Data communication
| Enabling SSL Certificate & exploring with HTTPS configurations | Simple | KSLOC | High | 6 | 8 | 10 | 9.6 | 1 | 1.2 | Implementation | Configuration management | To map the SSL certificate to the IIS virtual directory and to make sure it works well with the application
| Cyber Security Check List Document preparation | Simple | KSLOC | Low | 2 | 4 | 6 | 4 | 1 | 0.5 | Design | Project Planning | To prepare the Cyber security checklist
| OSS Scan and Support to Mini | Simple | KSLOC | Low | 8 | 10 | 12 | 10 | 1 | 1.25 | Design | Project Planning | To check and fullfill the OSS Scan and support to Mini
| Unit Testing | Simple | KSLOC | Low | 4 | 6 | 8 | 6 | 1 | 0.75 | Implementation | Coding | Writing unit test cases for the Hashing methods
| Code Reviews | Simple | KSLOC | Low | 2 | 4 | 6 | 4 | 1 | 0.5 | Testing | Review | Code and implementation review
| Rework/Bug fixing | Simple | KSLOC | Low | 10 | 12 | 10 | 11.3333 | 1 | 1.4167 | Implementation | Rework due to Defects | For Rework due to security implementation
| Integration Test | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Testing | To check the integration with UI application and the Back end application
| Code Coverage/Code Metrics | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Implementation | Project Monitoring and Control | To get the report of Code Coverage
| Support to UI/UX Developer | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Testing | Knowledge sharing to UI Developer on workflow
1
Component/Function <n> | DB Design and Table Creation | Medium | KSLOC | Medium
Implementation <subfunction/component>
| DB Design | Simple | KSLOC | Medium | 6 | 8 | 10 | 8 | 1 | 1 | Implementation | Coding | For the Database design and Schema. Averaged the estimation effort of all the DB tasks
| Table & Schema Creation | Simple | KSLOC | Medium | 4 | 4 | 8 | 4.6667 | 1 | 0.58333 | Implementation | Coding | For the Table creation. Averaged the estimation effort of all the DB tasks
| Creating Lookup tables and Data entry | Simple | KSLOC | Low | 4 | 4 | 8 | 4.6667 | 1 | 0.58333 | Implementation | Coding | For the Lookup Table creation. Averaged the estimation effort of all the DB tasks
| DB Reviews | Simple | KSLOC | Low | 2 | 2 | 4 | 2.3333 | 1 | 0.29167 | Testing | Review | DB Reviews for 3 API Interfaces
| Rework/Bug fixing | Simple | KSLOC | Low | 3 | 4 | 6 | 4.1667 | 1 | 0.52083 | Implementation | Rework due to Defects | For DB Design & Schema alterations
Product Integration
Product Integration Plan
Ensure Interface compatibility
Assemble Product Components
Software baselines
Alfa 1
Alfa 2
Alfa 3
Beta 1
Beta 2
Beta 3
Release Candidate
Release
Verification
Peer-reviews
Code Review <n>
Document Review <n>
Product Integration Test
Integration Test Description
Draft ready for internal review
Internal review draft
Draft ready for external review
External review draft
Final version for approval
Steco Approval
Test Environment
Test
Product Test
PTT
Preparation of Test Specification
Test Specification Internal review
Test specification external review
Test Specificatio review rework
Test environment setup
prePTT
Test execution
PTT | Review of test results
System Test
Preparation of Test Specification
Test Specification Internal review
Test specification external review
Test Specificatio review rework
Test environment setup
Test execution
preSTT
STT
Media Verification
Draft ready for internal review
Internal review draft
Draft ready for external review
External review draft
Final version for approval
Steco Approval
Test Environment
Test
Type Test List
Validation
Requirement Validation
Prototype
Demonstration to the Customer / customer representive
Review by Customer Representative (e.g., PLM, TPM)
Design Validation
UI Design Validation
Performance Validation
Maintainability
Review by Customer representative Technical Specialist
Interface Validation
Price Lists
Product Box
Version Lists
Document List
Product Bulletin
Release Notes
User Manuals
Manual 1
Preliminary Version
Review
Online Help
Ready for printing
Complete Status List
Document List
Product Bulletin
Release Notes
User Manuals
Manual 1
Preliminary Version
Review
Online Help
Ready for printing
Complete Status List
Total Work | [7 empty] | 424.75 |  | 53.0938
[8 empty] | (Person |  | (days)
hours)
Note on G11: Probablity Method of Estimation
Note on F12: ABB: Based on th Complexity of the task, the Average Effort in Column"I" will be Multiplied by addional factor of 1.2 in case of "High" complexity, by a factor of 1.1 in case the complexity of the task is "Medium" and by 1, when the task complexity is defined as "Low"
Note on C326: harikrishnan: Include the activities pertaining to product maintance. How to handled product enhancements (Service packs, Roll-ups)
Note on C327: harikrishnan: Design Review, Architecture Review
Note on C446: harikrishnan: If this effort is considered in the Verification PTT, no extra effort need to be considered.
Note on C452: harikrishnan: If this effort is considered in the Verification STT, no extra effort need to be considered.

## Guidelines
This Worksheet provides the input data for preparing the Project schedule:
Definitions:
Work Breakdown Structure (WBS) : A project Work Breakdown Structure is a fundamental methodology that divides the project into manageable elements of work. These elements of work are developed with increasing levels of detail to facilitate schedule development, resource assignment, cost estimation, risk management, and other project management concerns. To successfully plan a project, the WBS must completely list all tasks that must be performed for the project to achieve the desired results. Identify all included activities and basic data on these e.g. size and complexity.
WBS is used as input to Estimation.
A. Work Product : Any “tangible” product produced by a process. This may include files, documents and parts of the product, services, processes, specifications and invoices.
Work products are most likely to be subject to version control and configuration management.
The work products of a project are the artifacts the project produces (or uses) while working toward the final product.
Inputs to creation of WBS
- Product Requirements Specification
- Project Breakdown Structure
- WBS from earlier versions of the product from earlier versions for the product and previous projects, if available
- Implementation Proposals or similar documents
- Know-how from experienced personnel
Creating a WBS involves the following steps
-Start with the Project Breakdown Structure (work products)
-Break down all Work Products in the PBS into corresponding activities
* Review tasks include the effort for review meetings as well as rework based on the review.
Estimation Guidelines based on Past experience
Size estimates should be based on the Complexity of the tasks. Tasks shall be classified into "Low, Medium or High".
we will define a work product size as Simple-Low, when it is 10-15 pages or 500-1000 LOC
Medium-Medium, when it is 15-20 pages or 1000-1500 LOC
Complex-High, when it is greater than 20 pages or 1500 LOC
Also for the task other than documentation and implementation, the effort suggested in terms of percentage is as follows.
These are indicative and Project manager along with the team involved in Estimation shall decide the applicability as needed and apply appropriate factors.
Review of a document/code should be about 5 -10% of its preparation time.
Re-work of a document/code should be about 5 -10% of its preparation time
Project management activities should take 20% of the total project time
CM & QE activities should be about 5-10% of the total project time
Testing should be about 20 - 30% of the development time
Bug fixing should be about 20 - 30% of total development time
Please consider the following factors for your estimations:
1. Technology (C/ C++, Embedded, Development Platform (800xA), New technology)
2. Experience/Skill level of the resource to whom the task will be assigned / Else state if a specific task should be carried out by a resource with certain experience
3. Application knowledge and previous experience
4. Multisite development
Refer to 9ARD4-153 Measurement Repository as a gudieline for estimating the effort
Document the basis for estimations for various work products in the Comment column. Please answer the questions listed below to document the Estimation methods and basis.
B. WBS Element - is the activity, task or sub task required for creating the Work product.
Basis for Estimation :
C. Work Product Size - Specify the value for the size of the work product.
D. Unit of Measure - select the unit of measure for specifying the size of the work product. Size can be measured in terms of Lines of Code(KLOC), number of function points for software components for be developed, and in terms for Number of Pages for documents. Additional Units can be added, if required, in the Administration Worksheet of this template.
E. Complexity - Select the degree of complexity involved in producing the work product. Complecity can be specified in terms of High, Medium and Low.
The above basis for Estimation should be provided for all major tasks(specifically technical solution items). If applicable, you may provide a link to the detailed estimation worksheet for a task in the Comments column.
Estimated Person Hours : (Using Probablilty Method)
F. Optimistic - best case estimate
G. Most Likely - expected case estimate
H. Pessimistic - worst case estimate
I. Average Effort - is calculated as (Optimistic + 4(Most Likely) + Pessimistic) / 6
Based on th Complexity of the task, the Average Effort in Column"I" will be Multiplied by addional factor of 1.2 in case of "High" complexity, by a factor of 1.1 in case of "Medium" complexity and by 1 when the task complexity is defined as "Low"
J. No of Persons - Specify the number of Persons who will be assigned to the task.
K. Duration (Calendar days) - The duration (Calendar days) required to complete the task is calculated as
Average Effort / 8 / No of Persons. (assuming eight hours per day).
K. Phase: Select the listed phases appropriately (Scope Definition,Planning & Req Development, Design, Implementation, Testing, Closure)
L. Task Type: Select the listed task types appropriately (Requirements, Review, Rework due to Defects, Rework due to Changes, Design, Coding, Testing, User Manual, Project Planning, Project Monitoring and Control, Configuration management, Project Closure & Project related Training.)
M. Comments - add any useful comments related to the task or estimates. Capture the Assumptions, constraints and any other rationale for estimation in this column
Answer the following questions for your estimation :
How is the Work Breakdown Structure (WBS) organized? Functional?
Has any template project been used? What?
What methods have been used for estimating activity duration and planned working time?
Describe briefly how the volume/effort/cost was estimated.
How many people were involved in the estimation?
Experienced people?
Were any specific methods/principles used?
Similarity to other activities
Was estimation based on experiences from earlier projects? Which?
Historical database used - mention reference projects
Expert advice/Delphi technique/Three-point technique/Simulation, for example Monte Carlo
Describe the size estimation principle
How was size translated to effort?

## Administration
Work Product Size(UOM) | Complexity | Phase | Task Type
KSLOC | High | Scope Definition | Requirements
No of Function Points | Medium | Planning & Req Development | Review
No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects | No of Pages | Low | Design | Rework due to Defects
No of Tese Cases |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes |  |  | Implementation | Rework due to Changes
|  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design |  |  | Testing | Design
|  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding |  |  | Closure | Coding
|  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing |  |  |  | Testing
|  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual |  |  |  | User Manual
|  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning |  |  |  | Project Planning
|  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control |  |  |  | Project Monitoring and Control
|  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management |  |  |  | Configuration management
|  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure |  |  |  | Project Closure
|  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training |  |  |  | Project related Training
Note on C2: Documents that prepared during Pre G0, G0- G1
Note on C3: G1-G2
Note on C4: INSAV3: G2-G3
Note on G4: INSAV3: G2-G3
Note on K4: INSAV3: G2-G3
Note on O4: INSAV3: G2-G3
Note on S4: INSAV3: G2-G3
Note on W4: INSAV3: G2-G3
Note on AA4: INSAV3: G2-G3
Note on AE4: INSAV3: G2-G3
Note on AI4: INSAV3: G2-G3
Note on AM4: INSAV3: G2-G3
Note on AQ4: INSAV3: G2-G3
Note on AU4: INSAV3: G2-G3
Note on AY4: INSAV3: G2-G3
Note on BC4: INSAV3: G2-G3
Note on BG4: INSAV3: G2-G3
Note on BK4: INSAV3: G2-G3
Note on BO4: INSAV3: G2-G3
Note on BS4: INSAV3: G2-G3
Note on BW4: INSAV3: G2-G3
Note on CA4: INSAV3: G2-G3
Note on CE4: INSAV3: G2-G3
Note on CI4: INSAV3: G2-G3
Note on CM4: INSAV3: G2-G3
Note on CQ4: INSAV3: G2-G3
Note on CU4: INSAV3: G2-G3
Note on CY4: INSAV3: G2-G3
Note on DC4: INSAV3: G2-G3
Note on DG4: INSAV3: G2-G3
Note on DK4: INSAV3: G2-G3
Note on DO4: INSAV3: G2-G3
Note on DS4: INSAV3: G2-G3
Note on DW4: INSAV3: G2-G3
Note on EA4: INSAV3: G2-G3
Note on EE4: INSAV3: G2-G3
Note on EI4: INSAV3: G2-G3
Note on EM4: INSAV3: G2-G3
Note on EQ4: INSAV3: G2-G3
Note on EU4: INSAV3: G2-G3
Note on EY4: INSAV3: G2-G3
Note on FC4: INSAV3: G2-G3
Note on FG4: INSAV3: G2-G3
Note on FK4: INSAV3: G2-G3
Note on FO4: INSAV3: G2-G3
Note on FS4: INSAV3: G2-G3
Note on FW4: INSAV3: G2-G3
Note on GA4: INSAV3: G2-G3
Note on GE4: INSAV3: G2-G3
Note on GI4: INSAV3: G2-G3
Note on GM4: INSAV3: G2-G3
Note on GQ4: INSAV3: G2-G3
Note on GU4: INSAV3: G2-G3
Note on GY4: INSAV3: G2-G3
Note on HC4: INSAV3: G2-G3
Note on HG4: INSAV3: G2-G3
Note on HK4: INSAV3: G2-G3
Note on HO4: INSAV3: G2-G3
Note on HS4: INSAV3: G2-G3
Note on HW4: INSAV3: G2-G3
Note on IA4: INSAV3: G2-G3
Note on IE4: INSAV3: G2-G3
Note on II4: INSAV3: G2-G3
Note on IM4: INSAV3: G2-G3
Note on IQ4: INSAV3: G2-G3
Note on IU4: INSAV3: G2-G3
Note on C5: G3-G4
Note on G5: G3-G4
Note on K5: G3-G4
Note on O5: G3-G4
Note on S5: G3-G4
Note on W5: G3-G4
Note on AA5: G3-G4
Note on AE5: G3-G4
Note on AI5: G3-G4
Note on AM5: G3-G4
Note on AQ5: G3-G4
Note on AU5: G3-G4
Note on AY5: G3-G4
Note on BC5: G3-G4
Note on BG5: G3-G4
Note on BK5: G3-G4
Note on BO5: G3-G4
Note on BS5: G3-G4
Note on BW5: G3-G4
Note on CA5: G3-G4
Note on CE5: G3-G4
Note on CI5: G3-G4
Note on CM5: G3-G4
Note on CQ5: G3-G4
Note on CU5: G3-G4
Note on CY5: G3-G4
Note on DC5: G3-G4
Note on DG5: G3-G4
Note on DK5: G3-G4
Note on DO5: G3-G4
Note on DS5: G3-G4
Note on DW5: G3-G4
Note on EA5: G3-G4
Note on EE5: G3-G4
Note on EI5: G3-G4
Note on EM5: G3-G4
Note on EQ5: G3-G4
Note on EU5: G3-G4
Note on EY5: G3-G4
Note on FC5: G3-G4
Note on FG5: G3-G4
Note on FK5: G3-G4
Note on FO5: G3-G4
Note on FS5: G3-G4
Note on FW5: G3-G4
Note on GA5: G3-G4
Note on GE5: G3-G4
Note on GI5: G3-G4
Note on GM5: G3-G4
Note on GQ5: G3-G4
Note on GU5: G3-G4
Note on GY5: G3-G4
Note on HC5: G3-G4
Note on HG5: G3-G4
Note on HK5: G3-G4
Note on HO5: G3-G4
Note on HS5: G3-G4
Note on HW5: G3-G4
Note on IA5: G3-G4
Note on IE5: G3-G4
Note on II5: G3-G4
Note on IM5: G3-G4
Note on IQ5: G3-G4
Note on IU5: G3-G4
Note on C6: INSAV3: G4-G5
Note on G6: INSAV3: G4-G5
Note on K6: INSAV3: G4-G5
Note on O6: INSAV3: G4-G5
Note on S6: INSAV3: G4-G5
Note on W6: INSAV3: G4-G5
Note on AA6: INSAV3: G4-G5
Note on AE6: INSAV3: G4-G5
Note on AI6: INSAV3: G4-G5
Note on AM6: INSAV3: G4-G5
Note on AQ6: INSAV3: G4-G5
Note on AU6: INSAV3: G4-G5
Note on AY6: INSAV3: G4-G5
Note on BC6: INSAV3: G4-G5
Note on BG6: INSAV3: G4-G5
Note on BK6: INSAV3: G4-G5
Note on BO6: INSAV3: G4-G5
Note on BS6: INSAV3: G4-G5
Note on BW6: INSAV3: G4-G5
Note on CA6: INSAV3: G4-G5
Note on CE6: INSAV3: G4-G5
Note on CI6: INSAV3: G4-G5
Note on CM6: INSAV3: G4-G5
Note on CQ6: INSAV3: G4-G5
Note on CU6: INSAV3: G4-G5
Note on CY6: INSAV3: G4-G5
Note on DC6: INSAV3: G4-G5
Note on DG6: INSAV3: G4-G5
Note on DK6: INSAV3: G4-G5
Note on DO6: INSAV3: G4-G5
Note on DS6: INSAV3: G4-G5
Note on DW6: INSAV3: G4-G5
Note on EA6: INSAV3: G4-G5
Note on EE6: INSAV3: G4-G5
Note on EI6: INSAV3: G4-G5
Note on EM6: INSAV3: G4-G5
Note on EQ6: INSAV3: G4-G5
Note on EU6: INSAV3: G4-G5
Note on EY6: INSAV3: G4-G5
Note on FC6: INSAV3: G4-G5
Note on FG6: INSAV3: G4-G5
Note on FK6: INSAV3: G4-G5
Note on FO6: INSAV3: G4-G5
Note on FS6: INSAV3: G4-G5
Note on FW6: INSAV3: G4-G5
Note on GA6: INSAV3: G4-G5
Note on GE6: INSAV3: G4-G5
Note on GI6: INSAV3: G4-G5
Note on GM6: INSAV3: G4-G5
Note on GQ6: INSAV3: G4-G5
Note on GU6: INSAV3: G4-G5
Note on GY6: INSAV3: G4-G5
Note on HC6: INSAV3: G4-G5
Note on HG6: INSAV3: G4-G5
Note on HK6: INSAV3: G4-G5
Note on HO6: INSAV3: G4-G5
Note on HS6: INSAV3: G4-G5
Note on HW6: INSAV3: G4-G5
Note on IA6: INSAV3: G4-G5
Note on IE6: INSAV3: G4-G5
Note on II6: INSAV3: G4-G5
Note on IM6: INSAV3: G4-G5
Note on IQ6: INSAV3: G4-G5
Note on IU6: INSAV3: G4-G5
Note on C7: INSAV3: G5-G6,G6-G7
Note on G7: INSAV3: G5-G6,G6-G7
Note on K7: INSAV3: G5-G6,G6-G7
Note on O7: INSAV3: G5-G6,G6-G7
Note on S7: INSAV3: G5-G6,G6-G7
Note on W7: INSAV3: G5-G6,G6-G7
Note on AA7: INSAV3: G5-G6,G6-G7
Note on AE7: INSAV3: G5-G6,G6-G7
Note on AI7: INSAV3: G5-G6,G6-G7
Note on AM7: INSAV3: G5-G6,G6-G7
Note on AQ7: INSAV3: G5-G6,G6-G7
Note on AU7: INSAV3: G5-G6,G6-G7
Note on AY7: INSAV3: G5-G6,G6-G7
Note on BC7: INSAV3: G5-G6,G6-G7
Note on BG7: INSAV3: G5-G6,G6-G7
Note on BK7: INSAV3: G5-G6,G6-G7
Note on BO7: INSAV3: G5-G6,G6-G7
Note on BS7: INSAV3: G5-G6,G6-G7
Note on BW7: INSAV3: G5-G6,G6-G7
Note on CA7: INSAV3: G5-G6,G6-G7
Note on CE7: INSAV3: G5-G6,G6-G7
Note on CI7: INSAV3: G5-G6,G6-G7
Note on CM7: INSAV3: G5-G6,G6-G7
Note on CQ7: INSAV3: G5-G6,G6-G7
Note on CU7: INSAV3: G5-G6,G6-G7
Note on CY7: INSAV3: G5-G6,G6-G7
Note on DC7: INSAV3: G5-G6,G6-G7
Note on DG7: INSAV3: G5-G6,G6-G7
Note on DK7: INSAV3: G5-G6,G6-G7
Note on DO7: INSAV3: G5-G6,G6-G7
Note on DS7: INSAV3: G5-G6,G6-G7
Note on DW7: INSAV3: G5-G6,G6-G7
Note on EA7: INSAV3: G5-G6,G6-G7
Note on EE7: INSAV3: G5-G6,G6-G7
Note on EI7: INSAV3: G5-G6,G6-G7
Note on EM7: INSAV3: G5-G6,G6-G7
Note on EQ7: INSAV3: G5-G6,G6-G7
Note on EU7: INSAV3: G5-G6,G6-G7
Note on EY7: INSAV3: G5-G6,G6-G7
Note on FC7: INSAV3: G5-G6,G6-G7
Note on FG7: INSAV3: G5-G6,G6-G7
Note on FK7: INSAV3: G5-G6,G6-G7
Note on FO7: INSAV3: G5-G6,G6-G7
Note on FS7: INSAV3: G5-G6,G6-G7
Note on FW7: INSAV3: G5-G6,G6-G7
Note on GA7: INSAV3: G5-G6,G6-G7
Note on GE7: INSAV3: G5-G6,G6-G7
Note on GI7: INSAV3: G5-G6,G6-G7
Note on GM7: INSAV3: G5-G6,G6-G7
Note on GQ7: INSAV3: G5-G6,G6-G7
Note on GU7: INSAV3: G5-G6,G6-G7
Note on GY7: INSAV3: G5-G6,G6-G7
Note on HC7: INSAV3: G5-G6,G6-G7
Note on HG7: INSAV3: G5-G6,G6-G7
Note on HK7: INSAV3: G5-G6,G6-G7
Note on HO7: INSAV3: G5-G6,G6-G7
Note on HS7: INSAV3: G5-G6,G6-G7
Note on HW7: INSAV3: G5-G6,G6-G7
Note on IA7: INSAV3: G5-G6,G6-G7
Note on IE7: INSAV3: G5-G6,G6-G7
Note on II7: INSAV3: G5-G6,G6-G7
Note on IM7: INSAV3: G5-G6,G6-G7
Note on IQ7: INSAV3: G5-G6,G6-G7
Note on IU7: INSAV3: G5-G6,G6-G7

## Revision History
Rev. Ind | Page (P) | Description | Date | Dept/Init.
Naveenkumar Sreedharan |  | Created the first draft of WBS for Technical Solution | 2018-05-30 | IAMA Digital Products - APA User Management

## Change History (hidden)
Rev. Ind | Page (P) | Description | Date | Dept/Init.
-d0 | All | Initial Draft | 2006-04-17 | INCRC/PP Group/Apurva Singh
-d1 | All | Updated as per review comments in review meeting dated 2006-04-19 | 2006-04-20 | INCRC/PP Group/Apurva Singh
- | All | Initial Release | 2006-04-20 | INCRC/Q&P/Ashok V
Ad0 | All | Changes made as per review record for review meeting dated 2006-05-24 | 2006-04-25 | INCRC/PP Group/Apurva Singh
A | All | Review and Approved | 2006-07-12 | INCRC/Q&P/Tehzeeb A
Bd0 | All | Updated with standard template | 2007-01-08 | INCRC/PP Group/Apurva Singh
B | All | Approved | 2006-07-12 | INCRC/Q&P/Tehzeeb A
Cd0 | All | V&V process group have modified the WBS template to add validation related activities and Administration sheet is removed | 2007-01-08 | INCRC/PP Group/Apurva Singh
C | All | Approved | 2007-01-08 | INCRC/Q&P/Tehzeeb A
Dd0 | All | Validation work product is added with WBS Elements | 2007-01-09 | INCRC/PP Group/Apurva Singh
D | All | Approved | 2007-01-09 | INCRC/Q&P/Tehzeeb A
E0 | WBS & ESTIMATION | Added Phase and task Type fields | 2007-04-17 | INCRC/PP Group/Apurva Singh & Sathish
E1 | WBS & ESTIMATION | Modified phase "Requirements" to Planning & Req Development based on PP & PMC Process group review commnets | 2007-04-17 | INCRC/PP Group/Apurva Singh & Sathish
E2 | Guidelines | Updated Guidelines sheet appropriately | 2007-05-16 | INCRC/PP Group/Sathish
E | WBS & ESTIMATION and Guidelines | Approved | 2007-05-16 | INCRC/Q&P/A Tehzeeb
Fd0 | Guidelines | Included the below sub section under Sectin 'A': Based on Past experience Size estimates should be based on the Complexity of the tasks. Tasks shall be classified into "Low, Medium or High". we will define a work product size as Simple-Low, when it is 10-15 pages or 500-1000 LOC Medium-Medium, when it is 15-20 pages or 1000-1500 LOC Complex-High, when it is greater than 20 pages or 1500 LOC Also for the task other than documentation and implementation, the effort suggested in terms of percentage is as follows. These are indicative and Project manager along with the team involved in Estimation shall decide the applicability as needed and apply appropriate factors. Review of a document/code should be about 5 -10% of its preparation time. Re-work of a document/code should be about 5 -10% of its preparation time Project management activities should take 20% of the total project time CM & QE activities should be about 5-10% of the total project time Testing should be about 20 - 30% of the development time Bug fixing should be about 20 - 30%of total development time | 2007-06-13 | INCRC/PP Group/Dn Prasad & Ajay
Fd1 | WBS & ESTIMATION and Guidelines | Changes have made in Guidelines as under Section 'I. Average Effor": I. Average Effort - is calculated as (Optimistic + 4(Most Likely) + Pessimistic) / 6 Based on th Complexity of the task, the Average Effort in Column"I" will be Multiplied by addional factor of 1.2 in case of "High" complexity, by a factor of 1.1 in case of "Medium" complexity and by 1 when the task complexity is defined as "Low" As per the above defined the formula is updated in all Elements in WBS & Estimation Sheet | 2007-06-13 | INCRC/PP Group/Dn Prasad & Ajay
Fd2 | WBS & ESTIMATION and Guidelines | Reviewed Project Planning Group | 2007-06-14 | INCRC/PP Group
F | WBS & ESTIMATION and Guidelines | Approved | 2007-06-18 | INCRC/Q&P/A Tehzeeb
Gd0 | All | Added recommendation for estimating the complexity and size of work producted | 2007-11-13 | INCRC/PDI/DN Prasad
Gd1 | All | Reviewed Project Planning Group | 2007-12-07 | INCRC/PP Group
G | All | Approved | 2007-12-10 | INCRC/Q&P/A Tehzeeb
Hd0 | Administration Sheet | As suggested the by DN Prasad - fixed Technical related issue [Unit of Measure listbox (under Basis for Estimation section) in WBS & Estimation sheet is automatically updates based on the input of Work Product Size(UOM) section in Administration sheet] | 2008-02-22 | INCRC/Q&P/V Mani
H | Administration Sheet | Approved | 2008-03-06 | INCRC/Q&P/A Tehzeeb
I |  | Org. Name changed, File renamed for new convenetion | 2009-08-28 | INCRC / Q&P / Ramakrishnan G
J | Guidelines, WBS & Estimation Sheets | PCR-184: Guidelines Sheet updated for including the "estimation rationale" and "Assumptions & Constraints" of the Estimation in the 'Comments' Column. "Estimation" Sheet "Comments" Column Title changed to include Assumptions and rationale | 2010-07-07 | Ramakrishnan G
K | Guideline | PCR-287 : Added reference to Measurement Repository under section A | 2011-04-12 | Sathish V
L | WBS & Estimation | PCR-414,416 Included reference section for historical data | 2013-03-07 | Bharathi D
This worksheet must be removed while using the template as it is only used by "Author(s)/ Reviewer(s) / Approver(s)" of this document in order to track the change history of the template